## 23-02-2023
Work hour sheet 28/12/2022 - 23/02/2023
Student Name: | Zeke Zhang
date | start-time | finish-time | work-time(hr) | Comment
2022-12-28 | 16:00 | 17:30 | 1:30 | Create & setup project file and github repository
2023-01-05 | 15:00 | 17:00 | 2:00 | Incomplete attempt at timber matching algorithm testing with Alex script
2023-01-06 | 15:30 | 17:30 | 2:00 | Implemented CSV IO for read/write and added comparison feature for salvaged timber in Unity.
2023-01-20 | 14:00 | 19:30 | 5:30 | Imported Unity's timber framing logic into grasshopper script for enhanced flexibility and future scalability.
2023-01-21 | 16:00 | 19:30 | 3:30 | Implemented logic for opening position shift based on neighboring proximity and added meshing visualization for better understanding.
2023-01-22 | 13:00 | 13:30 | 0:30 | Optimized script by simplifying input parameters, grouping components into clusters and eliminating Python script for improved performance.
2023-01-24 | 17:00 | 20:00 | 3:00 | Integrated UDP socket for data communication between Grasshopper and Unity Engine.
2023-01-25 | 17:00 | 21:00 | 4:00 | Implemented CSV IO for reading and writing salvage timber list, added linear comparison for target timber frame matching.
2023-01-27 | 17:00 | 18:00 | 1:00 | Developed evaluation logic to calculate score based on evaluation of resulted data.
2023-01-31 | 17:00 | 19:00 | 2:00 | Improved comparison script performance with binary search and comparison logic implementation.
2023-02-01 | 17:00 | 18:00 | 1:00 | Implemented matching of timber frame outside tolerance values and formatted offcut lengths in output string.
2023-02-02 | 17:00 | 18:00 | 1:00 | Optimized evaluation algorithm to determine labor and material efficiency.
2023-02-08 | 17:00 | 19:00 | 2:00 | Add feature to match and reuse off-cut timber with length over 300mm - ensuring minimum length requirement met
2023-02-16 | 17:00 | 19:30 | 2:30 | fixed missing timber after matching process & calculation error, add material reuse efficiency calculation
2023-02-17 | 11:30 | 12:00 | 0:30 | Test upd socket, grasshopper <-> udp <-> unity realtime data communication
2023-02-23 | 17:30 | 20:30 | 3:00 | Set up a working unity training environment for future scaling and development, organized grasshopper scripts.
Total Hours |  |  | 1899-12-31 11:00
Formulas:
work-time(hr) = SUBTOTAL(109,Table2[work-time(hr)])

## 09-06-2023
Work hour sheet 23/05/2023 - 07/06/2023
Student Name: | Zeke Zhang |  |  | Repo: https://github.com/sean1832/Research-Assistance-ML-Assembly
date | start-time | finish-time | work-time(hr) | Comment
23/05/2023 | 11:30 | 20:30 | 9:00 | 1. A MAJOR CHANGE introducing a new C# class library, TimberAssembly.dll, in Visual Studio, improving code flexibility, modularity, and maintainability. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/2697398b424408313183884fda4c049ae4124a6e 2. Fixes to SecondMatch for issues causing incorrect return values and SecondMatch not skipping the matched subject. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/970d07df2f898cbd70382cf35a11cd7bc24291e1 3.The introduction of the 'SecondMatchFast' method, an optimization using HashSets for faster comparisons and reduced time complexity. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/bf98e92b4663b01eadc3355927f3248c0efaf175 4. A fix for IndexOutOfRangeException occurring when there are more Targets than Subjects. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/45e11ae3a4113fcb241848efb4d09c818e50c9b0 5. The OffCuts handling in MatchPair and Subjects list was revised to improve data organization. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/122b22d5de83571a80d829ab9dc406720df79f0f 6. The implementation of serialization for matched pairs, enhancing readability. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/5bba6c9590b9c81eb9bba7030000206d983fb264
24/05/2023 | 11:00 | 14:00 | 3:00 | 1. A fix for a false match occurring when the target dimension is smaller than a single subject. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/5d2e5c1e1ed998012b6ab55fbb751067ff9663ae 2. A fix to ensure RemainMatch doesn't return empty when the subject's dimension is larger than the targets. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/bf2a20fc7b6b2d1fb9f2dfde79ca2ba29dfd9c07
26/05/2023 | 19:00 | 23:30 | 4:30 | 1. A MAJOR CHANGE introducing a greedy 3D bin-unpacking algorithm method, 'CutToTarget'. Accompanying this, a new 'Processor' class has been added. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/980edd8240bdeedce6d2628c1cb8890ae32ad83a 2. Tests for 'CutToTarget' have been added, covering situations when the subject is smaller than the target, multiple subjects and targets, and when the subject is smaller than the target. 3. A refactor renaming 'Namespace Component' to 'Entities' and breaking down entities into 'Agent', 'Dimension', 'Pair', and 'Remain'. The 'Utilities' has been renamed to 'ComputeMatch'. 4. A refactor to modify entities methods, and match main function for improved readability. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/3639518e3a3c04438e660d02c7216c96c9f5d89d
28/05/2023 | 9:25 | 9:30 | 0:05 | 1. Modifies the visibility of the 'ComputeMatch' class, changing it to internal for better encapsulation in the build process. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/9c0792c4dfc1ac4bbe7ec4bc9749a5567d1c305f
2023-06-06 | 16:00 | 23:30 | 7:30 | 1. A MAJOR CHANGE involving the modification of the structure of entities. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/642a05e23f9be895492117c9f619a463665c90d2 2. A chore task to add 'todo' for 'thirdMatch' and 'fourthMatch' for future development. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/75f88528ae90151c55448b1a9fac6b0dfcb299d5 3. A chore task moving 'ComputeMatch' and 'Processor' to the Helper folder. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/fafc2e5550eec8bd3450d14d8131500e138404dd 4. A refactor updating the unit test name from 'UtilitiesTest' to 'ComputeMatchTest' for consistency. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/a0e7fbeb9b67a34e742b3b2bf64ad0e4b86ffe9d 5. The addition of new evaluation methods. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/a42220cc66ca393b74c7d959a435aba84be2b2c6 6. A feature introducing new methods to extract result data, with additions like 'GetUsedSubjectVolume', 'GetWasteVolume', 'GetSubjectInitVolume', and a refactor of 'GetWasteRateByVolume'. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/72f2327b716de0d0d831c01a5440eb25b330283d 7. The introduction of the 'ExtendToTarget' method, adding new timber when the salvage timber isn't long enough. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/0475871d2520689ebd0ba15074177c8be9723f6d 8. A build update to include XML documentation for builds. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/a2835b5a01b4e1c8085aae911935070021a1fad1 9. The addition of the 'GetNewSubjectVolume' method to calculate the total volume of new timbers. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/4449caf8d6038afd212ae66b8e1d4e7b76914507
2023-07-06 | 0:10 | 1:10 | 1:00 | 1. A fix for the 'ExtendToTarget' function where the new timber dimension was not matching the target orientation. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/c7624da1f786e8ad27e01022293c23d9650a2022 2. A feature update to the Unity script to accommodate new evaluation parameters. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/a746f549fa02a1978239ff178b6041e4ff97f0c1 3. A chore to set up for Unity UDP. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/b84e31355720d2ea445c7d2ad0e85d97097ca1a9
2023-07-06 | 17:00 | 18:00 | 1:00 | 1. A documentation update to add XML documentation, a chore to deprecate the 'RemainMatch' function, and a fix to 'ExtendToTarget' for correct handling of shared dimensions in the subject and target. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/916b868cfa30c22339ece43ea035396fefd4f720 2. A refactor to modify all Match methods' signatures in the 'Remain' class by replacing the 'out' parameter with 'ref' for better usage flexibility. https://github.com/sean1832/Research-Assistance-ML-Assembly/commit/45a6d95b88429f64c133626d1ed95f45bb5d6b1d
Total Hours |  |  | 1899-12-31 02:05
Formulas:
work-time(hr) = SUBTOTAL(109,Table24[work-time(hr)])